## Sheet1
Task Number | Task Name | Due Date | Completion Date | Status Task Due / Completed | Input date | Person Responsible | Status Open/Closed
1 | Processing of this transcript | 2021-12-17 | 2021-12-17 | Completed | 2021-12-17 | Mahathi | Closed
2 | Create this excel file with this list of tasks | 2021-12-17 | 2021-12-17 | Completed | 2021-12-17 | Mahathi | Closed
3 | Create a FlowChart | 2021-12-17 | 2021-12-18 | Completed | 2021-12-17 | Mahathi | Closed
4 | Scheduling the interview | 2021-12-20 | 0 | Due | 2021-12-17 | Prasun | Open
| Number of Closed Tasks | 3 |  |  |  |  | The number of Closed Tasks =3 and The number of Open Tasks = 1
| Number of OpenTasks | 1